1: What activities were completed during this reporting period?

- Participants attended workshops

- Gained new participants

- Used WRTP vehicle to transport WRTP Participants

- Updated flyers and brochures

- Completed ISPs for WRTP Participants

- Took participants to employers and drop off resumes

2: What activities are planned to be undertaken in the next reporting period?

- We plan to expand our program to new partners in the community.

- We plan to serve and enroll more participants.

- Have a faster process to now have individuals needing service be able to access them faster based on our partnerships in the community.

- Follow up with participants to see if they have had any success gaining employment or registering for education or training.

- Continue marketing to the Shasta County population.

- Collaborate with the radio station for marketing/outreach.

3: Describe any challenges or delays in implementation and course of action to address them.

- Participants not responding to our outreach, breakdown of communication. Continue communication in a reasonable manner.

- Participants not updating us on their successes. We will be telling them the importance of reaching back out on their successes and how it shows our program and how we are helping Shasta County.

4: What are you doing to achieve program expenditure deadlines?

- As mentioned last month, we received the lease prepayments. K2 has received the amount that was for 1255 Industrial.

- We continue to enroll participants in WRTP but are still looking for an additional Case Manager to help with our Round Mountain site.

- Continue to work on getting bids for the mobile unit. We purchased some training supplies that will help us train/educate participants.

5: Describe any successes this reporting period

- Workshops were conducted at Churn Creek to meet participant needs.

- Got new items for free from Shasta College (Table, drawers)

- Enrolled new participants

- Participants gained employment

6: Other Comments

- Took Treazure Aubrey for a second interview 11/7/2025

- Took Dani Atterberry to turn in her workers permit in for her job at Five and Below

- Zachary White and Hayleigh Austin received the Fire Tech Recognition of Perseverance award from Devin Lee

- CHYBA staff members helped with translation services at no cost.

- We are seeing great growth in the program and it is great to see our community wanting to partner with us.

- 6 WRTP participants gained employment