Activity completed during reporting period:

CHYBA staff: Fire Technology, Introduction to Medical Careers, and Medical Terminology classes have begun. These courses are part of their Career Technical Education (CTE) programs, which offer hands-on, work-based learning to prepare students with the skills and certifications required to meet industry-specific or nationally recognized employment standards. Staff completed Individualized Service Plans for all current WRTP participants. Program flyers and brochures have been updated to enhance community outreach. Participant training materials have been purchased, and work is ongoing to gather bids for building the mobile unit. All three site leases have been approved, and the advance check has been deposited; CHYBA will process lease payments as quickly as possible.

City staff: Conducted a site visit to observe Financial Literacy, Culinary, and Construction classes in action. Gained insight into course structures and saw students engaging in hands-on learning. Continued working with CHYBA to help them better understand the fiscal documentation required for invoice submissions, and dedicated significant time to auditing and monitoring funds.

Projected activity to be completed within the next 30 days:

CHYBA's enrollment and intake process has been streamlined, and they expect a quicker turnaround for participants to access services.

Challenges/delays:

CHYBA has faced challenges with potential participants not following up or responding to outreach efforts. The organization will continue trying to contact these individuals. Marketing efforts via social media have been delayed because website policies require linking pages to individual users; CHYBA is actively working to resolve this. The City has also delayed approving CHYBA's monthly invoices due to insufficient detail in the backup documentation. However, several invoice issues have been resolved, and we are working closely with CHYBA to ensure proper compliance with financial reporting standards.

Project Highlights:

CHYBA's WRTP staff attended a job fair to connect with potential participants and community providers. WRTP participants in the culinary program prepared meals for a community event, during which the program manager gave a presentation on the program. One participant used a supportive service to pick up clothes for a job interview; three participants gained part-time employment (they wish to receive ongoing training until they achieve their goal of full-time employment); and two homeschooled participants joined the Construction and Culinary programs.

* Notes - The corresponding financial report does not include any CHYBA expenditures. Their most recent invoice is still being processed by the City and should be included next month.

The numbers in the Supportive Services totals (19) are correct for this reporting period. 12 participants utilized 19 Supportive Services this month.

The number of applicants to the program is the same as the number of enrollments this month. CHYBA explained that while many people are casually interested in the program, only those who are serious about enrollment complete the enrollment application.

The number of persons enrolled this month in each training category is only 6, the other 6 participants enrolled this month have not chosen an education path yet and are only receiving supportive services at this time.